## Product Backlog
ID | Theme | As a/an | I want to… | so that… | Notes | Priority | Sprint # | Status
1 | Simulator | Player | Play a game made up of fixed-duration turns | I have only a limited time to decide what to buy and sell | This is an essential property of the game. | 1 | 1 | DONE
2 | Simulator | Player | Know how many turns have passed since the start of the game | I know how far into the game I am |  |  | 4 | TODO
3 | Simulator | Player | Have a fixed number of turns in a game | The game has a fixed duration. | We don’t want the game to go on forever… |  | 4 | TODO
4 | Simulator | Player | See variation between the prices of shares in the market. | Share prices do not always change at the same rate/have the same price. | This is the stock value model | 1 | 1 | DONE
5 | Game | Player | be able to buy shares | they can make money | This needs refinement |  | 3 | TODO
6 | Game | Player | be able to see the current price of shares | they can decide what to buy/sell |  | 1 | 1 | DONE
7 | Game | Player | be able to sell shares | they can earn profit | This is an essential property of the game. |  | 3 | TODO
8 | Simulator | Player | see history of buy/sell transaction | I can improve my knwoladge of market | This will help for the palyer future investments |  | 3 | TODO
9 | Simulator | Player | see current active transaction | I can buy more quantiy or sell | This will show the current unsold sahres of the player |  | 3 | TODO
10 | Simulator | Player | search the valid stock in the market | I can buy shares what I like | Player can search stocks and buy shares |  | 1 | DONE
11 | Simulator | Player | see the current winner | I can get the target |  |  | 4 | TODO
12 | Game | Player | bank account | I can maintain balance | This is an essential property of the game. | 1 | 2 | DONE
13 | Simulator | Player | see current account balance | they can build a stratergy according to the bank balance | This will increase the comfortability of the player | 2 | 2 | DONE
14 | Simulator | Player | see share price history | I can analyze old market values and build a stratergy | This will helps to the player to gain more profits | 1 | 1 | DONE
15 | Game | Player | get an advices from an expert(ANALYST) | I can get some good ideas,helps about some hard situation. | This will helps to the player to reduce the risks |  | 4 | TODO
16 | Game | Player | select a player from player list created | I can play the game with selected ones | can create multiple players |  | 3 | TODO
17 | Game | Bank | tell if they don't have sufficient balance | player can be informed |  |  | 2 | DONE
18 | Game | Bank | withdraw money for player to buy shares | player can earn more profit | When player need buy shares he withdraw money from bank | 1 | 2 | DONE
19 | Game | Bank | deposit money | account update with new balace | when player sell shares profit or loss update the account | 1 | 2 | DONE
20 | Simulator | Analyzer | guide and advice to the players. | they can solve their problems with our help. | This will helps to the player to reduce the risks |  | 4 | TODO
21 | Simulator | Analyzer | know everything about value changing algorithms | they can easily help players to find jackpots | This will helps to the player to gain more profits |  | 4 | TODO
22 | Simulator | Analyzer | gain my knowledge about value changings each time. | they can improve their knowledge to help players | This Improves the probability of getting best advices from experts |  | 4 | TODO
23 | Game | Broker | organize and maintans transaction between bank and player | they can get the history of tarnsaction | This is an essential property of the game. | 1 | 2 | DONE
24 | Game | Broker | maintain records about shares buy/sell by player | they can analyze old market values and suggest best options to player | This will improves the probability of finding best shares |  | 3 | TODO
25 | Game | Computer Player | play a game in each turn | player can play with computer player | This will help player as a guide |  | 3 | TODO

## Sprint 1
Sprint Goal: | Aiming for a D grade
Start Date: | 2018-05-20
End Date: | 2018-05-26
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
As a Player, I want to play a game made up of fixed-duration turns so that I have only a limited time to decide what to buy and sell | 1 | T1.1 | Research how to create a fixed-duration turn based game | 4 | 5 | 5
|  | T1.2 | Design a solution for this game | 2 | 3 | 3
|  | T1.3 | Create Test Cases | 5 | 2.5 | 2.5
|  | T1.4 | Implement the solution | 6 | 2 | 2
As a Player, I want to see variation between the prices of shares in the market.so that share prices do not change at the same rate/have the same price. | 4 | T4.1 | Read the Project Spec | 3 | 2.5 |  | 2.5
|  | T4.2 | Design the stock market simulator | 4 | 5 |  | 5
|  | T4.3 | Create Test Cases | 5 | 2.5 |  |  | 2.5
|  | T4.4 | Implement the design | 7 | 3 |  |  | 3
As a Player, I want to be able to see the current price of shares so that they can decide what to buy/sell | 6 | T6.1 | Storyboard a UI to show this information | 2.5 | 2 |  |  | 2
|  | T6.2 | Design a Service to expose this information | 2 | 3 |  |  |  | 3
|  | T6.3 | Create Test Cases | 2 | 1 |  |  |  | 1
|  | T6.4 | Implement the Service | 3 | 4 |  |  |  | 4
|  | T6.5 | Implement the UI | 2 | 4 |  |  |  | 1 | 3
|  | T6.6 | Connect the Service to the UI | 2 | 1.5 |  |  |  |  | 1.5
As a Player, I want to search the valid stock in the market so that I can buy shares what I like | 10 | T10.1 | Storyboard a UI to show this information | 1.5 | 1 |  |  |  |  | 1
|  | T10.2 | Design a Service to expose this information | 2 | 2 |  |  |  |  | 2
|  | T10.3 | Create Test Cases | 1 | 1.5 | [5 empty] | 1.5
|  | T10.4 | Implement the Service | 2 | 3 | [5 empty] | 3
|  | T10.5 | Implement the UI | 3 | 2 | [5 empty] | 2
|  | T10.6 | Connect the Service to the UI | 1 | 1 | [5 empty] | 1
As a Player, I want to see share price history so that I can analyze old market values and build a stratergy | 14 | T14.1 | Storyboard a UI to show this information | 2 | 1.5 | [6 empty] | 1.5
|  | T14.2 | Design a Service to expose this information | 2 | 1 | [6 empty] | 1
|  | T14.3 | Create Test Cases | 2 | 1.5 | [6 empty] | 1.5
|  | T14.4 | Implement the Service | 3 | 2 | [6 empty] | 2
|  | T14.5 | Implement the UI | 4 | 3 | [6 empty] | 3
|  | T14.6 | Connect the Service to the UI | 1 | 1 | [6 empty] | 1
|  |  | Sprint Countdown: | 74 | 61.5 | 12.5 | 7.5 | 7.5 | 9 | 7.5 | 7.5 | 10

## Sprint 1 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
fixed duration time | stock market price variation | display stock price variation
diplay current stock prices
search stock prices
display line chart for stock values
display history of share price
General Reflections
All the functions that are implemented work fine.

## Sprint 2
Sprint Goal: |  | Aiming for a C grade
Start Date: | 2018-05-27
End Date: | 2018-06-02
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
As a Player I want to bank account so that I can maintain balance. | 12 | T12.1 | Design databse to store data | 1 | 0.5 | 0.5
|  | T12.2 | Design a Service to handle incoming request | 2 | 1.5 | 1.5
|  | T12.3 | Create Test Cases | 3 | 2 | 2
|  | T12.4 | Implement the Service | 2 | 2 | 2
As a Player I want to see current account balance so that they can build a stratergy according to the bank balance | 13 | T13.1 | Storyboard a UI to show this information | 2 | 1.5 |  | 1.5
|  | T13.2 | Design a Service to expose this information | 1.5 | 1 |  | 1
|  | T13.3 | Create Test Cases | 2 | 2 |  | 2
|  | T13.4 | Implement the Service | 2 | 1 |  | 1
|  | T13.5 | Implement the UI | 2 | 3.5 |  | 2 | 1.5
|  | T13.6 | Connect the Service to the UI | 3 | 3 |  |  | 3
As a Bank I want to tell if they don't have sufficient balance so that player can be informed | 17 | T17.1 | Design a Service | 1 | 1 |  |  |  | 1
|  | T17.2 | Create Test Cases | 1 | 1.5 |  |  |  | 1.5
|  | T17.3 | Implement the Service | 2 | 1 |  |  |  | 1
|  | T17.4 | Connect the Service to the UI | 1.5 | 1 |  |  |  | 1
As a Bank I want to withdraw money for player to buy shares so that player can earn more profit | 18 | T18.1 | Design a Service for this | 2 | 3.5 |  |  |  |  | 3.5
|  | T18.2 | Create Test Cases | 3 | 3 |  |  |  |  | 3
|  | T18.3 | Implement the Service | 2 | 2.5 |  |  |  |  | 2.5
As a Bank I want to withdraw money for player to buy shares so that player can earn more profit | 19 | T19.1 | Design a Service for this | 2 | 3 | [5 empty] | 3
|  | T19.2 | Create Test Cases | 3 | 1.5 | [5 empty] | 1.5
|  | T19.3 | Implement the Service | 2 | 2 | [5 empty] | 2
As a Broker I want to organize and maintance transaction between bank and player so that they can get the history of tarnsaction | 23 | T23.1 | Design databse to store data | 1 | 0.5 | [6 empty] | 0.5
|  | T23.2 | Design a Service | 3 | 3.5 | [6 empty] | 3.5
|  | T23.3 | Create Test Cases | 4 | 3 | [6 empty] | 3
|  | T23.4 | Implement the Service | 4 | 3 | [6 empty] | 3
|  |  | Sprint Countdown: | 52 | 48 | 6 | 7.5 | 4.5 | 4.5 | 9 | 6.5 | 10

## Sprint 2 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
Bank account and broker account create succesfuly
Withdraw and deposit services work perfectly
Display player account balance
Broker maintain players buy and sell transaction perfectly
General Reflections
All function ae implemented are work perfectly

## Sprint 3
Sprint Goal: | Aiming for a B grade
User Story | PBL ID# | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | Sprint Countdown: | 0 | 0 | 0 | 0 | 0

## Sprint 3 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections

## Sprint 4
Sprint Goal: | Aiming for a A grade
User Story | PBL ID# | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | Sprint Countdown: | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 4 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections